## Analytics
|  |  | Projected | Actual | Remainder |  | Row Labels | Count of Risk
progress | 40% |  | 576000 | 284200 | 291800 |  | High | 14
budget | 50.66% | [5 empty] | Medium | 18
schedule | On Schedule | [5 empty] | Low | 28
[7 empty] | Grand Total | 60
|  |  | Row Labels | Count of Status
151 |  |  | Complete | 24
151 |  |  | In Progress | 22 |  |  | Row Labels | Count of Issue
0% |  |  | Not Started | 14 |  |  | Revision | 8
40% |  |  | Grand Total | 60 |  |  | Unresolved | 10
[7 empty] | Pending | 18
[7 empty] | Resolved | 24
40% ahead |  |  | Status | Tasks | Projected Cost | Actual Cost | Grand Total | 60
|  |  | Not Started | 14 | 93000 | 0
|  |  | In Progress | 22 | 366000 | 166000
|  |  | Complete | 24 | 117000 | 118200
| PROJECTS / TASKS |  |  |  | BUDGET
| Not Started | In Progress | Complete |  | PROJECTED | ACTUAL | REMINDER
| 14 | 22 | 24
Total Task
60

## Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
PROJECT TOPIC
TOTAL SALES

## project data
Task ID | Task Name | Department | Status | Start Date | End Date | Budgeted | Actual | Risk | Issue
T101 | Market Analysis | Marketing | Complete | 2025-01-01 | 2025-01-15 | 5000 | 4800 | Low | Resolved
T102 | Site Audit | IT | Complete | 2025-01-05 | 2025-01-20 | 8000 | 8200 | Medium | Resolved
T103 | App Wireframes | IT | In Progress | 2025-01-10 | 2025-02-15 | 15000 | 7000 | Low | Revision
T104 | Hiring Campaign | HR | In Progress | 2025-01-15 | 2025-03-01 | 12000 | 5000 | High | Pending
T105 | Legal Review | Legal | Not Started | 2025-02-01 | 2025-02-15 | 3000 | 0 | Medium | Unresolved
T106 | SEO Content | Marketing | Complete | 2025-01-02 | 2025-01-20 | 4500 | 4500 | Low | Resolved
T107 | Server Setup | IT | In Progress | 2025-01-20 | 2025-03-15 | 25000 | 12000 | High | Pending
T108 | Onboarding Doc | HR | Not Started | 2025-03-01 | 2025-03-15 | 2000 | 0 | Low | Pending
T109 | Budget Audit | Finance | Complete | 2025-01-01 | 2025-01-10 | 3500 | 3400 | Low | Resolved
T110 | UI Testing | IT | Not Started | 2025-03-15 | 2025-04-15 | 9000 | 0 | Medium | Unresolved
T111 | Social Media Ads | Marketing | In Progress | 2025-01-10 | 2025-02-28 | 10000 | 6000 | Low | Revision
T112 | Data Migration | IT | In Progress | 2025-01-25 | 2025-04-01 | 30000 | 15000 | High | Pending
T113 | Safety Training | Operations | Complete | 2025-01-05 | 2025-01-15 | 6000 | 6200 | Medium | Resolved
T114 | Procurement | Operations | In Progress | 2025-01-20 | 2025-03-10 | 18000 | 9000 | Low | Pending
T115 | Compliance Check | Legal | Not Started | 2025-03-01 | 2025-03-20 | 5000 | 0 | High | Unresolved
T116 | Brand Refresh | Marketing | In Progress | 2025-01-15 | 2025-04-01 | 22000 | 11000 | Medium | Revision
T117 | Security Patch | IT | Complete | 2025-01-10 | 2025-01-12 | 2500 | 2500 | Low | Resolved
T118 | Inventory Sync | Operations | Not Started | 2025-04-01 | 2025-04-15 | 7500 | 0 | Low | Pending
T119 | PR Outreach | Marketing | Complete | 2025-01-01 | 2025-01-25 | 8000 | 8500 | High | Resolved
T120 | Cloud Backup | IT | In Progress | 2025-02-01 | 2025-03-01 | 11000 | 4000 | Medium | Pending
T121 | Staff Workshop | HR | Complete | 2025-01-10 | 2025-01-12 | 4000 | 4000 | Low | Resolved
T122 | Client Contract | Legal | In Progress | 2025-01-20 | 2025-02-15 | 6000 | 3000 | Medium | Revision
T123 | API Docs | IT | Not Started | 2025-04-10 | 2025-05-10 | 5000 | 0 | Low | Unresolved
T124 | Focus Groups | Marketing | In Progress | 2025-02-01 | 2025-03-15 | 14000 | 6000 | High | Pending
T125 | Logistics Plan | Operations | Complete | 2025-01-15 | 2025-01-30 | 9000 | 8800 | Low | Resolved
T126 | Code Review | IT | Complete | 2025-01-05 | 2025-01-10 | 3000 | 3100 | Low | Resolved
T127 | Email Setup | IT | Complete | 2025-01-01 | 2025-01-03 | 1000 | 900 | Low | Resolved
T128 | Vendor Sourcing | Operations | In Progress | 2025-02-10 | 2025-04-01 | 20000 | 5000 | Medium | Pending
T129 | Lead Gen | Marketing | Not Started | 2025-05-01 | 2025-06-01 | 15000 | 0 | Medium | Unresolved
T130 | Risk Assessment | Legal | Complete | 2025-01-10 | 2025-01-20 | 4000 | 4200 | High | Resolved
T101 | Market Analysis | Marketing | Complete | 2025-01-01 | 2025-01-15 | 5000 | 4800 | Low | Resolved
T102 | Site Audit | IT | Complete | 2025-01-05 | 2025-01-20 | 8000 | 8200 | Medium | Resolved
T103 | App Wireframes | IT | In Progress | 2025-01-10 | 2025-02-15 | 15000 | 7000 | Low | Revision
T104 | Hiring Campaign | HR | In Progress | 2025-01-15 | 2025-03-01 | 12000 | 5000 | High | Pending
T105 | Legal Review | Legal | Not Started | 2025-02-01 | 2025-02-15 | 3000 | 0 | Medium | Unresolved
T106 | SEO Content | Marketing | Complete | 2025-01-02 | 2025-01-20 | 4500 | 4500 | Low | Resolved
T107 | Server Setup | IT | In Progress | 2025-01-20 | 2025-03-15 | 25000 | 12000 | High | Pending
T108 | Onboarding Doc | HR | Not Started | 2025-03-01 | 2025-03-15 | 2000 | 0 | Low | Pending
T109 | Budget Audit | Finance | Complete | 2025-01-01 | 2025-01-10 | 3500 | 3400 | Low | Resolved
T110 | UI Testing | IT | Not Started | 2025-03-15 | 2025-04-15 | 9000 | 0 | Medium | Unresolved
T111 | Social Media Ads | Marketing | In Progress | 2025-01-10 | 2025-02-28 | 10000 | 6000 | Low | Revision
T112 | Data Migration | IT | In Progress | 2025-01-25 | 2025-04-01 | 30000 | 15000 | High | Pending
T113 | Safety Training | Operations | Complete | 2025-01-05 | 2025-01-15 | 6000 | 6200 | Medium | Resolved
T114 | Procurement | Operations | In Progress | 2025-01-20 | 2025-03-10 | 18000 | 9000 | Low | Pending
T115 | Compliance Check | Legal | Not Started | 2025-03-01 | 2025-03-20 | 5000 | 0 | High | Unresolved
T116 | Brand Refresh | Marketing | In Progress | 2025-01-15 | 2025-04-01 | 22000 | 11000 | Medium | Revision
T117 | Security Patch | IT | Complete | 2025-01-10 | 2025-01-12 | 2500 | 2500 | Low | Resolved
T118 | Inventory Sync | Operations | Not Started | 2025-04-01 | 2025-04-15 | 7500 | 0 | Low | Pending
T119 | PR Outreach | Marketing | Complete | 2025-01-01 | 2025-01-25 | 8000 | 8500 | High | Resolved
T120 | Cloud Backup | IT | In Progress | 2025-02-01 | 2025-03-01 | 11000 | 4000 | Medium | Pending
T121 | Staff Workshop | HR | Complete | 2025-01-10 | 2025-01-12 | 4000 | 4000 | Low | Resolved
T122 | Client Contract | Legal | In Progress | 2025-01-20 | 2025-02-15 | 6000 | 3000 | Medium | Revision
T123 | API Docs | IT | Not Started | 2025-04-10 | 2025-05-10 | 5000 | 0 | Low | Unresolved
T124 | Focus Groups | Marketing | In Progress | 2025-02-01 | 2025-03-15 | 14000 | 6000 | High | Pending
T125 | Logistics Plan | Operations | Complete | 2025-01-15 | 2025-01-30 | 9000 | 8800 | Low | Resolved
T126 | Code Review | IT | Complete | 2025-01-05 | 2025-01-10 | 3000 | 3100 | Low | Resolved
T127 | Email Setup | IT | Complete | 2025-01-01 | 2025-01-03 | 1000 | 900 | Low | Resolved
T128 | Vendor Sourcing | Operations | In Progress | 2025-02-10 | 2025-04-01 | 20000 | 5000 | Medium | Pending
T129 | Lead Gen | Marketing | Not Started | 2025-05-01 | 2025-06-01 | 15000 | 0 | Medium | Unresolved
T130 | Risk Assessment | Legal | Complete | 2025-01-10 | 2025-01-20 | 4000 | 4200 | High | Resolved